## Sheet1
2016 Garage Sale Planning Sheet |  | Target Date | Who | Note or reference
Date for Garage Sale |  | June 3-4 Friday and Saturday |  | http://www.greenmountainestates.org/2016-garage-sale.html
Preparations
| Create spreadsheet to record address and merchandise offered | 2015-05-15 | Dave M | * Add QR code to the spreadsheet (will be the same QR code each year; will tie to link for current year of website
| Post merchandise list on web as it changes | May 15 thru June 5 | Dave M | Update weekly so Mary can stop by with goodie bags ASAP
| Announce sale and solicit merchandise list | Start May 15 | Dave M | We'll use Contact@GreenMountainEstates.org and Murphy's phone # * Promote use of QR code for most current list/paperless route
| Create map for sale and post addresses | Start May 15 | Dave M | * Add 3 map distro locations to the map: North entrance, South entrance, Ohio (vehicle pullout in front of Foothills Elementary) * Add QR code to the map
| 3 Entrance Signs for Merchandise Lists and Maps | May 25 | Mary | Print shop * Laminate one color copy of the map in case the stands run out * Simplify & laminate title sign - bigger type "GARAGE SALE MAP"
| Hang large vinyl registration signs at 2 entrances | 3 weeks in advance | Mary | Hang with tomato stakes or stronger poles
| Prepare arrow signs for finding houses | May 25 | Mary | Print shop; * ADD BALLOONS TO EACH FOR VISIBILITY; paint arrow RED for visibility
| Directional Signs: 1. Union, 2. Alameda/Safeway, 3. Alameda/Las Fuentes | May 25 | Mary | * Create 3 neon arrows with "30+ family sale!" arrow * Post arrow on medians, especially on Union **Add balloon sticks to all signs
| Facebook invitation | 2016-05-29 | Mary | To engage/possibly get an idea of how many are interested
| Facebook ad | Start May 15 | Mary
| Place Craigslist ad | May 29 | Dave M | http://www.greenmountainestates.org/2014-garage-sale.html
| Place Denver Post ad | May 29 | Dave M
| Place Nextdoor notice | May 29 | Dave M
| Please Ad with 9News | May 29 | Dave M | http://www.9news.com/life/style/colorado-guide/love-garage-sales-find-one- in-your-neighborhood-or-upload-yours/230415170
Thursday night
| Copy merchandise list and map | June 4 | Mary | 2016: used 150 copies; feedback was that maps weren't easy to locate once the balloons popped so probably safe to print 200 each with better sign visibility * Email each participant the final PDF of the map/list (or add to their packet?) * Some participants requested a stack of maps to distribute during the sale
| Place Union and 2 Alameda Signs |  | Mary | Neon Arrows @ 5am
| Place Entrance Signs at Cedar, Ohio, and Beech/Alkire |  | Mary | Check Friday evening to replenish copies
| Distribute neighborhood arrows (team?) |  | Mary/Diane
Friday- show time
| Balloons | June 5 | Mary | With sticks, balloons can be assembled the night before - no helium needed. Replace any deflated balloons on Friday night. $12 for 144 sticks https://www.amazon.com/Fun-Express-Premium-Quality-Balloon/dp/B007BDDK5Q
Saturday June 6 at end of sale
| Collect signs from Union, Alameda & Beech | June 6 | Mary | Pick up signs at 4 pm on Saturday
| Collect Entrance signs from Cedar, Ohio & Beech |  | Mary | Pick up signs at 4 pm on Saturday
| Collect all arrows |  | Mary/Diane | Pick up signs at 4 pm on Saturday
| Send follow up email | 2016-06-07 | Mary | Any suggestions for next year?
2016 Feedback:
We had a fair amount of success. We heard from many, many of our buyers asking where maps were, not enough signs.
...the previous year’s signage had more pop - old-school red and white signs that most people recognize. Easy to ID. These blended into the background.
Awesome job !! Thanks for all the hard work you put in on this project....
hello mary, was nice to meet you. and about the sign you did a good job, but the ballons will work because the signs were small and if a car was there then you couldnt see the sign. also i put one at alameda and safeway on railing and also buy the estate sale so that they would keep coming up center and also i put one by wahoo taco in the middle median, next time it would be nice to put one the baclk side of kings. hopefully you can make the signs higher, tahnks for all your help, ive did this 30 plus years and signs make the sale. see you next year, it takes a lot of time. darla
Mary's note: 3 arrows were taken some time during the weekend - 1 from Alkire, 1 from Safeway, and 1 from Braun Cir.
| LARGE VINYL SIGN FOR THE 2 ENTRANCE STONES: |  | DIRECTIONAL SIGNS (DIANE HAS ABOUT 20)
| QR CODE FROM QR STUFF: |  | DIRECTIONAL SIGNS (MARY HAS ABOUT 20) - paint these arrows RED
| * Will need to renew registration to re-use the code |  | ** Not pictured: 3 wooden A-Frames to hold the maps/address list
** Create 3 neon posterboard arrows saying, "30+ family garage sale" for Alameda/Union